## Slide 1
Five decisions made, zero deferred — fastest design sprint in the program; Phase 2 scope now locked.
Phase 2 Design Sprint · May 15, 2026 · 14 attendees · 6 hours
May 15, 2026
Phase 2 Design Sprint
WHAT WE DID
1. Aligned on data architecture principles 2. Reviewed 3 integration options 3. Completed stakeholder impact mapping 4. Ran friction log review (47 items) 5. Prioritized backlog top-20
WHAT WE DECIDED
1. Adopt API-first integration pattern 2. Defer mobile app to Phase 3 3. Appoint Change Lead (Maya Chen) 4. Extend sprint by 2 weeks for QA 5. Approve $320K contingency draw
WHAT'S NEXT
1. Architecture design review (May 22) 2. Vendor kickoff — DataCo (May 24) 3. User story grooming (May 28) 4. Steering committee update (June 2) 5. Phase 3 planning begins (June 15)
Phase 2 scope locked. Five decisions taken in one session — no deferrals, no escalations. Next hard gate: architecture review May 22.
Source: [add source here or delete]
148