## Slide 1
ACCENTURE INTERNAL
DRAFT
SPRINT RETROSPECTIVE · SAILBOAT
Velocity is strong but three risks need mitigation — anchor items from sprint 4 must be resolved before Phase 2 launch
💨
SAIL & WIND — WHAT PROPELLED US
· Strong stakeholder alignment kept priorities stable across all sprints · Pre-built accelerators saved 3 weeks of custom development effort · Team velocity improved 40% from sprint 1 to sprint 4
🏝️
ISLAND — GOALS & VISION
· Deliver Phase 2 on time by end of Q3 · 100% user adoption across all business units · Reduce defect rate to <2% in production
⚓
ANCHOR — WHAT SLOWED US
· Legacy system dependencies blocked three sprint deliverables · Unclear requirements in sprint 4 caused two rework cycles · 3 team members on leave reduced capacity by 25% in weeks 6-8
🪨
ROCKS — RISKS AHEAD
· Integration testing window is tight - only 4 days before Phase 2 freeze · Budget variance likely if scope creeps beyond current sprint plan · Key stakeholder availability drops in July - decisions may stall
SO WHAT
Velocity is strong and the island is in sight — but three anchor items from sprint 4 and a tight integration window must be resolved before Phase 2 launch or the rocks will stop us.
CONFIDENTIAL — ACCENTURE INTERNAL
Slide Lab · 2026 · 150