## Slide 1
Integration testing is the critical path risk — Phase 2 go-live slides to Q4 2025 if not resolved by Week 3
Implementation tracker · 10 milestones across 5 workstreams · target vs. actual/forecast
#
MILESTONE
WORKSTREAM
TARGET DATE
ACTUAL / FORECAST
STATUS
% COMPLETE
01
Project kickoff
All
15 Jan 2025
15 Jan 2025
COMPLETE
100%
02
Architecture design approved
Technology
28 Feb 2025
7 Mar 2025
COMPLETE (LATE)
100%
03
Phase 1 pilot launch
Operations
1 Apr 2025
1 Apr 2025
COMPLETE
100%
04
Data migration Wave 1
Data
15 May 2025
20 May 2025
COMPLETE (LATE)
100%
05
Training program begins
People
1 Jun 2025
1 Jun 2025
ON TRACK
65%
06
Integration testing complete
Technology
15 Jul 2025
1 Aug 2025
AT RISK
30%
07
Phase 2 UAT
All
1 Sep 2025
TBD
DELAYED
0%
08
Phase 2 go-live
All
1 Oct 2025
TBD
DELAYED
0%
09
Phase 3 planning
Program
1 Nov 2025
TBD
NOT STARTED
0%
10
Program closure
All
31 Mar 2026
TBD
NOT STARTED
0%
CRITICAL PATH
Integration testing is the critical path risk — Phase 2 go-live slides to Q4 2025 if not resolved by Week 3.
1. [add footnote here or delete]
Source: [add source here or delete]
154