## Slide 1
Pilot Results Summary
Performance outcomes, qualitative findings, and lessons learned from the field pilot
PILOT OVERVIEW
Location
Northeast Region — 4 Sites
Duration
8 Weeks (Mar – May 2026)
Participants
142 End Users · 6 Admins
QUANTITATIVE RESULTS
Process Cycle Time
14.2 days
8.7 days
▲ 39%
Error Rate (per 1,000 transactions)
23.1
9.4
▲ 59%
User Satisfaction Score (NPS)
+18
+54
▲ 200%
QUALITATIVE FINDINGS
✓
Frontline staff found the redesigned workflow significantly easier to navigate — onboarding time dropped by half in observed sessions.
✓
Integration with existing ERP required minimal rework; IT teams rated the deployment complexity as "lower than expected" in exit interviews.
△
Exception-handling for edge cases (legacy vendor codes) required manual intervention in ~7% of transactions — volume is manageable but warrants automation.
LESSONS LEARNED
WHAT WORKED
Dedicated change-champion network accelerated adoption in sites 2 and 3 by mobilising peer-to-peer coaching.
WHAT WORKED
Phased data migration reduced go-live risk; zero critical data-loss incidents recorded across all four sites.
TO IMPROVE
Expand exception-rule library before full rollout to reduce manual overrides; assign a dedicated triage owner per region.
RECOMMENDATION
Proceed to full rollout — pilot results meet all success thresholds. Incorporate 2 modifications before scale-up.
• Automate legacy vendor-code exception handling prior to Wave 2 launch
• Replicate change-champion model across all remaining regions
1. [add footnote here or delete]
Source: [add source here or delete]
196