## Slide 1
Client Program Needs a Decisive Pivot Before Q3 Gate
Executive Summary — Program Health Review · May 2026
CONTEXT
The Orion transformation program entered Phase 3 four months ago with three workstreams running in parallel. Despite on-schedule delivery of two streams, the data migration workstream has accumulated a 6-week lag, putting the Q3 go-live at material risk. Steering has not yet been formally notified of scope implications.
FINDINGS
1
Data migration lag is systemic — root cause is an under-resourced ETL team, not a tooling defect; adding sprint cycles will not close the gap without headcount.
2
Change management readiness scores dropped from 74% to 61% in the last pulse survey, signaling user adoption risk at launch.
3
Budget contingency is 80% consumed with two months remaining; current burn rate projects a $1.2M overrun unless scope is re-baselined.
RECOMMENDATION
Approve a 6-week schedule extension and immediate resource augmentation for the data workstream to protect go-live quality and contain budget exposure.
› Onboard 2 senior ETL engineers from the bench by end of May to restore migration velocity to target. › Re-baseline scope with Steering at the June 3 gate to formally absorb the extension and reset the budget ceiling.
NEXT STEPS
Raise resource request for 2 ETL engineers through the Talent Deployment board.
J. Reyes · Delivery Lead
May 23
Prepare revised program baseline (schedule + budget) for Steering deck.
A. Müller · PMO
May 30
Present extension recommendation and re-baselined plan at Steering gate.
C. Okafor · Sponsor
Jun 3
1. [add footnote here or delete]
Source: [add source here or delete]
208