## Slide 1
Account scorecard — Q3 FY26 program health
PROGRAM HEALTH
Prometheus
ON TRACK
KEY HIGHLIGHTS
› 1,000+ automation use cases; 42% deployed across 14 archetypes › MS 2.0 pre-requisites complete — go-live confirmed 3/16 › 85%+ MS activation; final 15% on track for Q3 close › GenAI: 3,800+ GitHub Copilot users active
Fairway — EU Mod
AT RISK
KEY HIGHLIGHTS
› SIT complete; UAT3 starting — 3-week slip risk on cutover › TSA Exit planning initiated; resourcing gap flagged for steering › Go-live May 5th — contingency plan for May 19th › 16 weeks to production; cutover events on schedule
Journey 2 Cloud
ON TRACK
KEY HIGHLIGHTS
› 45 resources mobilized; Phase 1 design approved › Phase 2 architecture underway — Q4 FY26 migration start › $7.9M FY26 benefit on track; no material blockers
Tech Mod / Hire-to-Retire
AT RISK
KEY HIGHLIGHTS
› Joint Mod Council established; governance guardrails pending › AIQ: 10,000+ courses complete; exec 1:1 coaching active › Portfolio modernization — benefit at risk without Q3 decision
1. [add footnote here or delete]
Source: [add source here or delete]
23