## Slide 1
Phoenix Programme · Week 12 of 24 · Steering Committee decision required.
Four workstreams tracked. One is blocked. This slide asks for a go/no-go on the critical path replan.
12 / 24
WEEK
94%
BUDGET UTILIZED
3
ISSUES OPEN
2
RISKS RED
WORKSTREAM STATUS
Data Migration
ON TRACK
847K records migrated, target 1.2M — velocity on plan, delta-load testing complete
Process Design
ON TRACK
14 of 18 future-state flows signed off — remaining 4 in business review this week
Change & Training
AT RISK
LMS build delayed 2 weeks — vendor dependency; contingency plan in review, go-live buffer not yet consumed
Integration & Testing
BLOCKED
UAT environment not provisioned — IT access request pending 18 days; blocks full regression cycle by Week 16
DECISION REQUIRED
UAT environment is 18 days overdue. How should the programme proceed on the critical path?
APPROVE
Escalate IT provisioning to CTO today — maintains Week 16 regression window, no schedule slip
DEFER
Accept 2-week regression compression — increases defect-escape risk, go-live moves to Week 26
ESCALATE
Invoke programme governance board — triggers formal replanning and revised business case approval
1. [add footnote here or delete]
Source: [add source here or delete]
256