## Slide 1
Sprint 14 · Two-week delivery plan
Day-by-day task allocation across workstreams — 19 May to 30 May 2026
SPRINT 14 GOAL:
Complete API integration layer and user acceptance testing for module 3.
19 May – 30 May 2026
WORKSTREAM
Week 1 · Mon 19 – Fri 23 May
Week 2 · Mon 26 – Fri 30 May
DAY
Mon 19
Tue 20
Wed 21
Thu 22
Fri 23
Mon 26
Tue 27
Wed 28
Thu 29
Fri 30
UX Design
Wireframes & flows
UAT screens
Frontend Dev
API integration UI
Backend Dev
API layer build · full sprint
QA Testing
Test cases · regression · UAT sign-off
Data Engineering
Pipeline & schema setup
Stakeholder Review
Review
BLOCKERS
AUTH SERVICE: OAuth token refresh intermittent failure in staging — DevOps investigating.
MODULE 3 SPEC: Final acceptance criteria not signed off — Product Owner review requested by Wed 21.
SPRINT VELOCITY
42
pts committed
38
pts completed last sprint
Velocity trend: ↑ improving — team capacity stable across both weeks
1. [add footnote here or delete]
Source: [add source here or delete]
283