## Slide 1
Project Charter — Digital Supply Chain Transformation
One-page charter for executive alignment and project initiation approval
PROJECT NAME
Supply Chain Digital Twin
SPONSOR
R.J. (CFO)
PROJECT MANAGER
M.P. (Delivery Lead)
START DATE
01 Jun 2026
END DATE
28 Feb 2027
STATUS
Initiation
OBJECTIVES
1
Establish a real-time digital twin of end-to-end supply chain operations across 12 distribution centres
2
Reduce inventory holding costs by 18% through AI-driven demand sensing and replenishment automation
3
Enable executive-level supply risk visibility with a configurable tier-2 supplier monitoring dashboard
SCOPE
IN SCOPE
SAP ERP integration and real-time data pipeline (12 DCs)
AI demand-sensing model training, validation and deployment
Executive risk dashboard (Power BI) with tier-1 and tier-2 supplier data
OUT OF SCOPE
Manufacturing execution system (MES) integration
Retail point-of-sale feed and last-mile logistics optimisation
SUCCESS CRITERIA
Inventory holding cost reduction
≥ 18%
Order fulfilment accuracy rate
≥ 99.2%
Dashboard adoption (weekly active users)
≥ 85%
System uptime SLA (production environment)
99.5%
KEY STAKEHOLDERS
RJ
Rachel Jensen
Executive Sponsor · CFO
MP
Mario Peralta
Project Manager · Delivery Lead
SO
Sandra Okonkwo
Business Owner · VP Supply Chain
TK
Thomas Krause
Tech Lead · Enterprise Architecture
KEY MILESTONES
01 Jun 26
Project kick-off and team onboarding complete
15 Aug 26
SAP data pipeline live across all 12 distribution centres
30 Oct 26
AI demand model validated and deployed to staging
28 Feb 27
Full platform go-live and hypercare period ends
BUDGET
Technology & Licensing
$620,000
Professional Services
$1,140,000
Change Management & Training
$185,000
TOTAL BUDGET
$1,945,000
1. [add footnote here or delete]
Source: [add source here or delete]
349