## Slide 1
DECISION REQUIRED · HTR INITIATIVES
Accenture rolls off May 31 — Finance readiness on HTR initiatives determines coverage risk.
Event up top, status in the middle, the binary ask at the bottom. Owner column makes the handoff explicit; Harvey balls show current progress.
PROGRESS
0%
~25%
~50%
~75%
Done
⚑ PROJECT ROLLOFF
May 31, 2026
Finance committed to own remaining HTR initiatives post-rolloff
Initiative
Owner
Status
Comments
Background Checks Cost Reduction
Client Finance
~25%
Vendor RFP issued; awaiting bids
Cost Per Hire Optimization
Client Finance
NOT STARTED
Owner unconfirmed — needs assignment
Sourcing channel rationalization
Client Finance
~50%
Pilot underway in 2 regions
Onboarding automation
Client Finance
NOT STARTED
Awaiting tool selection
Vendor consolidation (Tier 2)
Client Finance
~25%
Inventory complete; negotiation pending
DIRECTION NEEDED
Continue Accenture support past May 31
Define scope · duration · revised SOW
OR
Transition to Finance as planned
Confirm Finance readiness by May 31
1. [add footnote here or delete]
Source: [add source here or delete]
58