## Slide 1
RISK REGISTER · PILOT
Risk register — six tracked, two reds with mitigation owners.
Detail backing the heat map: each risk has impact/likelihood, current RAG, owned mitigation, and a single accountable name. Ordered by RAG, reds on top.
RAG
GREEN
AMBER
RED
#
RISK DESCRIPTION
IMPACT
LIKELIHOOD
RAG
MITIGATION
OWNER
R1
Stakeholder withdrawal mid-pilot
H
M
RED
“MD weekly check-in”
MP
Mario
R2
Scope creep beyond pilot charter
H
H
RED
“Charter signed at kickoff”
MR
Maria
R3
Tooling provisioning delay
M
L
AMBER
“Pre-arranged with IT”
PM
PMO
R4
Vendor (Claude) outage
H
L
AMBER
“Offline mode for build”
EN
Engineering
R5
Resistance from senior consultants
M
M
AMBER
“Coach pairing”
MP
Mario
R6
Junior team can't ramp on toolchain
M
M
GREEN
“Onboarding session run W1”
CO
Coach
SO WHAT
Two reds, both with mitigation owners assigned. Watch for week-3 status — if either stays red, escalate to steering.
1. [add footnote here or delete]
Source: [add source here or delete]
86