## Slide 1
WORKSTREAMS × PHASES
Four workstreams × four phases — sixteen plays.
Each cell names the play that workstream runs in that phase. Read down for a workstream's arc; across for a phase end-to-end.
CURRENT PHASE
Pilot phase
WORKSTREAM
SETUP
PHASE 1
PILOT
PHASE 2
SCALE
PHASE 3
SUSTAIN
PHASE 4
WS 1
Strategy
Define success metrics
Align on scope & guardrails
Weekly check-ins
Steer mid-pilot pivots
Quarterly review
Reset targets per practice
BAU governance
Annual strategy refresh
WS 2
Build
Tool provisioning
Skeleton library v1
Live pattern library use
Rapid iteration on gaps
HTML → PPTX engine
Self-serve onboarding
Pattern contributions
Quarterly release cadence
WS 3
Coach
Onboarding plan
Recruit pilot consultants
Daily coaching
Office hours & pairing
Coach certification
Train-the-trainer rollout
Champion community
Peer review rituals
WS 4
Measure
Baseline capture
Instrument the workflow
Weekly scorecard
Qualitative feedback loop
Cross-practice scorecard
Benchmark vs. baseline
Annual ROI
Value story refresh
SO WHAT
Sixteen plays, one program. Every workstream owes the Pilot column its full attention this quarter — Scale and Sustain only land if Phase 2 proves the model.
1. [add footnote here or delete]
Source: [add source here or delete]
87