## Slide 1
Pilot status · Week 3 · Green overall, three decisions needed.
EXECUTIVE SUMMARY
WEEK 3 OF 4 · STEERING COMMITTEE
OVERALL STATUS
WEEK 3 OF 4
KEY WINS THIS PERIOD
4 WINS
KEY RISKS
3 OPEN
DECISIONS NEEDED
3 ASKS
GREEN
ON TRACK
Pilot on track for all 4 success metrics. No escalations this week. Wave 2 scope ready for steering approval.
✓
Cycle time −64% vs baseline — exceeded 50% target
✓
94% first-review sign-off — target was 85%
✓
All 4 pilot users actively engaged, no drop-offs
✓
Pattern library at 80 patterns; on track for 100 by EOM
⚑
Amber: 2 senior managers still ramping — coaching scheduled this week
⚑
Amber: CFO transition mid-pilot — stakeholder re-alignment underway
⚑
Red: IT provisioning for Wave 2 not started — blocks 6/1 kickoff
⚑
Amber: Vendor SOW renewal lagging — legal review still pending
1
Approve Wave 2 scope (+12 users, 3 new use cases)
MARIO · BY FRI
2
Greenlight pattern library investment to 100 patterns
MD · BY FRI
3
Hire 1 designer-engineer to sustain pattern velocity
HR · BY NEXT WEEK
Three items need MD decision by Friday — without them, Wave 2 slips two weeks.
1. [add footnote here or delete]
Source: [add source here or delete]
88