## Slide 1
Wave 2 change readiness — awareness is there, ability isn't.
ADKAR scoring across the consulting org: people know Slide Lab exists and roughly half want it, but knowledge and ability gaps will stall adoption unless coaching and reinforcement land before Wave 2 kicks off.
ADKAR READINESS MODEL · N = 142 RESPONDENTS · SURVEY + MANAGER INTERVIEWS, APR 2026
A
AWARENESS
Know the change is happening and why.
CURRENT LEVEL
4 / 5
ON TRACK
Most consultants know Slide Lab exists; town hall and MD email drove broad reach.
D
DESIRE
Want to participate and support the change.
CURRENT LEVEL
3 / 5
WATCH
~50% actively want it; the other half see it as "another tool" on top of existing workflow.
K
KNOWLEDGE
Know how to change — the skills and steps.
CURRENT LEVEL
2 / 5
GAP
Only the 14 champions know how it actually works; no enablement materials yet for the broader org.
A
ABILITY
Can demonstrate the change in real work.
CURRENT LEVEL
2 / 5
GAP
Low — first attempts stall on framing and briefs; needs structured coaching, not just docs.
R
REINFORCEMENT
Sustain the change — recognition, metrics, rituals.
CURRENT LEVEL
2 / 5
GAP
Scoreboard exists but nobody watches it; no MD recognition tied to Slide Lab usage.
OVERALL READINESS
65%
0%
25%
50%
75%
100%
NEEDS WORK
Awareness is solved; the next 6 weeks have to move K, A, and R from red to amber — or Wave 2 launches into an org that can't actually use the tool.
1. [add footnote here or delete]
Source: [add source here or delete]
94